## Governance and Compliance
Risk Description | Risk Owner | Initial Risk Score | Residual Risk Score | Mitigating Actions | Action Status | Risk Status | Review Date
Failure to comply with Charity Commission Regulations | PCC | 6 | 3 | Annual check against Charity Commisssion requirements | On-going | Annual review | 2027-04-01
Failure to meet Safeguarding requirements | PCC, PSO (Clare) | 12 | 4 | 1. Regular checks by safeguarding team. 2. Introduction of Dashboards | Complete | Annual Review | 2027-04-01
Lack of Insurance cover or gaps in policy | PCC, Treasurer | 8 | 6 | Annual review by treasurer | On-going | Annual review | 2027-04-01
Failure to comply with GDPR and data protection law | PCC, Administrator | 6 | 4 | 1.Annual GDPR compliance check. 2. Implement cookies policy. 3. Implement updated data privacy notice. 4. Check if registration with ICO is required. | Complete | Annual Review | 2027-04-01
Inadequate oversight or accountability of church funds | PCC, Treasurer | 16 | 8 | 1. Treasurer in post 2. Finance governance committee in place 3. Reports scrutinized by PCC 4. PCC members DBS checked 5. Bank Identity checks in place for PCC 6. External audit of accounts by reputable accountancy firms | Complete | Annual review | 2027-04-01

## People and Volunteers
Risk Description | Risk Owner | Initial Risk Score | Residual Risk Score | Mitigating Actions | Action Status | Risk Status | Review Date
Injury or accidents involving staff, volunteers, or visitors | PCC, Administrator | 12 | 8 | Annual review of risk assessments. | On-going | Annual review | 2027-05-01
Insufficient training or supervision of volunteers | PCC, Vicar | 9 | 6 | 1. Training in place | Complete | Annual Review | 2027-05-01
Lack of safeguarding checks for appropriate roles | PCC, PSO (Clare) | 12 | 4 | 1. Regular checks by safeguarding team. 2. Introduction of Dashboards | Complete | Annual review | 2027-05-01
Burnout or unavailability or key volunteers or clergy | PCC, Vicar, Wardens | 20 | 16 | 1. Increase focus from PCC. 2. Clarifying expectations through documentation. 3. Support for volunteers from clergy. | On-going | Annual Review | 2027-05-01
False allegations being made against individuals, the church, or the PCC | PCC, Vicar, Wardens | 8 | 4 | Church policies in place | Complete | Annual review | 2027-05-01
Conflicts of interest or misconduct | PCC, Vicar, Wardens | 8 | 4 | Standing agenda item for the PCC | Complete | Annual review | 2027-05-01
Medical emergency | PCC, Vicar, Wardens | 9 | 6 | Plans in place | Complete | Annual review | 2027-05-01

## Buildings and Property
Risk Description | Risk Owner | Initial Risk Score | Residual Risk Score | Mitigating Actions | Action Status | Risk Status | Review Date
Poor maintenance or unsafe church buildings | PCC, Administrator | 16 | 12 | Annual review of risk assessments. | On-going | Annual review | 2027-06-01
Fire risk, electrical faults, or structural hazards | PCC, Administrator | 8 | 4 | 1. Regular electrical checks (PAT testing). 2. Introduction of fire strategy. | Complete | Annual Review | 2027-06-01
Slips, trips, and falls | PCC, Administrator | 9 | 6 | 1. Annual check of risk assessments. 2. Regular checks of hazards in church, hall and churchyard. | On-going | Annual review | 2027-06-01
Security of the church and theft of valuables | PCC, Vicar, Wardens | 8 | 4 | 1. Church , hall and grounds securely locked when not in use. 2. Use of SMART water | Complete | Annual review | 2027-06-01
Asbestos or hazardous materials present | PCC, Vicar, Wardens | 4 | 4 | 1. Asbestos report for church 2. Risk assessments in place | On-going | Annual review | 2027-06-01

## Service & Events
Risk Description | Risk Owner | Initial Risk Score | Residual Risk Score | Mitigating Actions | Action Status | Risk Status | Review Date
Overcrowding or poor crowd management | PCC, Vicar, Wardens | 6 | 3 | 1. Church wardens and stewards available for regular events 2. Extra stewards volunteers recruited for special events e.g. Carol Service 3. Risk assessments for fire safety and evacuation plans | Complete | Annual Review | 2027-07-01
Inadequate fire evacuation procedures | PCC, Vicar, Wardens | 8 | 4 | 1. Fire evacuation plan to be agreed with PCC 2. Fire risk assessment in place | Ongoing | Annual Review | 2027-07-01
Unsafe use of candles or electrical equipment | PCC, Vicar, Wardens | 8 | 4 | 1. Church and hall hire terms and conditions 2. Fire risk assessment 3. Electrical equipment testing | Complete | Annual Review | 2027-07-01
Poorly managed external hires or third-party use of premises | PCC, Administrator | 6 | 4 | 1. Updated church and hall hire terms and conditions 2. Updated deposit protocol 3. Church administrator in regular contact with users | Complete | Annual Review | 2027-07-01
SPK Groups
Bible Tots (age 0 to Reception) | PCC, Vicar, Wardens | 12 | 8 | 1. All volunteers recruited via safer recruitment including training and DBS checks 2. Under 2’s accompanied by parent or carer if necessary 3. Mandated adult to child ratio (minimum 1:3) 4. Electrical sockets protected with covers 5. First aid equipment available 6. Age-appropriate toys available | Complete | Annual Review | 2027-07-01
Seekers (Reception to school year 2) | PCC, Vicar, Wardens | 12 | 8 | 1. All volunteers recruited via safer recruitment including training and DBS checks 2. Two volunteers mandated as minimum for this group. 3. Mandated adult to child ratio (minimum 1:6) 4. Children are positioned away from radiator and television 5. First aid equipment available 6. Age-appropriate craft equipment used | Complete | Annual Review | 2027-07-01
Diggers (school year 3-6) | PCC, Vicar, Wardens | 12 | 8 | 1. All volunteers recruited via safer recruitment including training and DBS checks 2. Two volunteers mandated as minimum for this group. 3. Mandated adult to child ratio (minimum 1:6) 4. All cutting equipment is stored away from child access 5. Age-appropriate craft equipment used 6. Filing cabinets are kept locked and secured 7. First Aid equipment is available | Complete | Annual Review | 2027-07-01
Spark (school year 7 -10) | PCC, Vicar, Wardens | 8 | 4 | 1. All volunteers recruited via safer recruitment including training and DBS checks. 2. Two volunteers mandated as minimum for this group 3. Mandated adult to child ratio (minimum 1:8) 4. Fire risk assessments 5. Fire evacuation plan 6. First Aid equipment available | Complete | Annual Review | 2027-07-01
Ignite (school year 11-14) | PCC, Vicar, Wardens | 8 | 4 | 1. All volunteers recruited via safer recruitment including training and DBS checks 2. Two volunteers mandated as a minimum for this group. 3. Mandated adult to child ratio (minimum 1:10) 4. Fire risk assessments 5. Fire evacuation plan 6. First aid equipment available | Complete | Annual Review | 2027-07-01

## External & Environmental
Risk Description | Risk Owner | Initial Risk Score | Residual Risk Score | Mitigating Actions | Action Status | Risk Status | Review Date
Extreme weather (floods, storms) damaging property | PCC, Vicar, Wardens | 12 | 8 | 1. Sandbags by south door to prevent flooding. 2. Thorough check of property after extreme weather | Complete | Annual Review | 2027-08-01
Local crime or anti-social behaviour near church | PCC, Vicar, Wardens | 12 | 9 | 1. High St gates to be kept locked whenever possible. 2. North Hill gates to be kept locked unless people on-site. 3. Use of SmartWater | Complete | Annual Review | 2027-08-01
Reputation risk from controversial public statements or actions | PCC, Vicar, Wardens | 9 | 3 | 1. Welcome, dignity and fair treatment policy drafted 2. Code of conduct to be agreed by PCC | On-going | Annual review | 2017-08-01
Pandemics or health outbreaks | PCC | 4 | 4 |  |  |  | 2027-08-01

## Financial
Risk Description | Risk Owner | Initial Risk Score | Residual Risk Score | Mitigating Actions | Action Status | Risk Status | Review Date
Dependency on external grants or income sources | PCC, Treasurer | 12 |  |  | On-going | PCC Review | 2027-09-01
Fraud or theft | PCC, Vicar, Wardens | 9 | 3 | 1. All PCC members are DBS checked 2. Finance governance committee in place 3. External accountant audit 4. Bank required identity checks in place | Complete | Annual Review | 2027-09-01
Inadequate financial controls or oversight | PCC, Treasurer | 6 | 3 | 1. Review by treasurer and PCC 2. Standing agenda item for PCC | On-going | Annual review | 2027-09-01
Sudden drop in regular giving or donations | PCC, Treasurer | 12 |  |  | On-going | PCC Review | 2027-09-01
Over-reliance on a few donors | PCC, Treasurer | 12 |  |  | On-going | PCC Review | 2027-09-01
Unplanned major expenditure (eg emergency repairs) | PCC, Treasurer | 16 |  |  | On-going | PCC Review | 2027-09-01

## IT & Data
Risk Description | Risk Owner | Initial Risk Score | Residual Risk Score | Mitigating Actions | Action Status | Risk Status | Review Date
Cybersecurity threats (eg phishing, ransomware) | PCC, Administrator | 3 | 3 | 1. IG Policy 2. Assessment of personal Data use | Complete | Annual Review | 2027-10-01
Loss of data (eg contacts, gift aid records) | PCC, Administrator | 3 | 3 | 1. Regular back up of data on flash drives (stored offsite) | Complete | Annual Review | 2027-10-01
No backup or recovery plan for digital assets | PCC, Administrator | 9 | 3 | backup of data on flash drives (stored offsite) | Complete | Annual Review | 2027-10-01
Improper use of social media or website content | PCC, Administrator | 6 |  |  | On-going | PCC Review | 2027-10-01

## Operational & Strategic
Risk Description | Risk Owner | Initial Risk Score | Residual Risk Score | Mitigating Actions | Action Status | Risk Status | Review Date
Unclear mission or lack of strategy | PCC, Vicar | 12 |  |  | On-going | PCC Review | 2026-06-01
Poor succession planning for key roles | PCC, Vicar, Wardens | 12 |  |  | On-going | PCC Review | 2026-06-01
Failure to engage or grow the congregation | PCC, Vicar, Wardens | 12 |  |  | On-going | PCC Review | 2026-06-01
Lack of capacity to deliver new projects | PCC, Vicar, Wardens | 16 |  |  | On-going | PCC Review | 2026-06-01
Dependence on ageing congregation or volunteers | PCC, Vicar, Wardens | 9 |  |  | On-going | PCC Review | 2026-06-01

## C of E issues
Risk Description | Risk Owner | Initial Risk Score | Residual Risk Score | Mitigating Actions | Action Status | Risk Status | Review Date
Division within congregation re issues relating to LLF | PCC, Vicar, Wardens | 15 | 5 | 1.careful teaching on sexuality & LLF 2.clarity re St Peter’s theological position 3. awareness of importance of parish profile | Complete | PCC Review
Compelled to leave the CofE | PCC, Vicar | 15 | 5 | support for CEEC and engagement with synodical processes | Complete | PCC Review